## Test_Roadmap
Phase | Module / Feature | Test Types | Planned Start | Planned End | Actual Start | Actual End | Status | Notes
Planning | All Modules | Test Planning | 2025-11-01 | 2025-11-14 | 2025-11-01 | 2025-11-14 | Completed | Test Plan & Roadmap created
Analysis & Design | Cart | UI + API + DB Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 8 UI test cases designed
Analysis & Design | Checkout | UI + API Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 13 UI test cases designed
Analysis & Design | Payment | UI + API Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 7 UI test cases designed
Analysis & Design | Confirmation | UI Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 4 UI test cases designed
Analysis & Design | Sign-up | UI + API + DB Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 14 UI + 7 API test cases
Analysis & Design | Contact | UI Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 14 UI test cases designed
Analysis & Design | Login | UI + API Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 7 UI + 6 API test cases
Analysis & Design | Home | UI Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 5 UI test cases designed
Analysis & Design | Products API | API Test Case Design | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28 | Completed | 14 API endpoints covered
Implementation | Cart | UI Execution + Automation | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-05 | Completed | 8/8 test cases executed
Implementation | Checkout | UI Execution + Automation | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-07 | Completed | 13/13 test cases executed
Implementation | Payment | UI Execution + Automation | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-08 | Completed | 7/7 test cases executed
Implementation | Confirmation | UI Execution | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-06 | Completed | 4/4 test cases executed
Implementation | Sign-up | UI + API Execution | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-09 | Completed | 14/14 UI + 7/7 API tests
Implementation | Contact | UI Execution | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-10 | Completed | 14/14 test cases executed
Implementation | Login | UI + API Execution | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-08 | Completed | 7/7 UI + 6/6 API tests
Implementation | Home | UI Execution | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-07 | Completed | 5/5 test cases executed
Implementation | All APIs | API Test Execution | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-11 | Completed | 96/96 API tests executed
Implementation | Database | DB Test Execution | 2025-11-29 | 2025-12-12 | 2025-11-29 | 2025-12-10 | Completed | 8/8 DB tests executed
Test Completion | All Modules | Regression Testing | 2025-12-13 | 2025-12-26 | 2025-12-13 | 2025-12-20 | In Progress | Critical bugs blocking release
Test Completion | All Modules | UAT Validation | 2025-12-13 | 2025-12-26 | 2025-12-21 | 2025-12-26 | Not Started | Waiting for regression completion
Test Completion | All Modules | Performance Testing | 2025-12-13 | 2025-12-26 | 2025-12-18 | 2025-12-26 | Not Started | JMeter scripts ready
Test Completion | All Modules | Release Validation | 2025-12-13 | 2025-12-26 | 2025-12-26 | 2025-12-26 | Not Started | Final sign-off pending

## Sprint_Summary
Sprint Number | Sprint Duration | Modules Covered | Test Cases Executed | Passed | Failed | Blocked | Bugs Raised | API Tests Executed | Automation Scripts Added | Summary / Notes
Sprint 1 | 2025-11-01 to 2025-11-14 | Planning Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Test Plan & Roadmap established. Project foundation set.
Sprint 2 | 2025-11-15 to 2025-11-28 | All Modules | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 75 manual test cases designed. 96 API test cases created. Jira integration completed.
Sprint 3 | 2025-11-29 to 2025-12-12 | All Modules | 179 | 158 | 21 | 0 | 23 | 96 | 45 | 75 UI + 96 API + 8 DB tests executed. 23 bugs found. Automation framework started.
Sprint 4 | 2025-12-13 to 2025-12-26 | All Modules | 85 | 65 | 15 | 5 | 8 | 45 | 30 | Regression in progress. Payment issues critical. 30 automation scripts added.